## 🗓 30-Day Timeline
PLANORA — LAUNCH PLAN ¦ April 15 → May 15, 2026
Week | Dates | Area | Task / Deliverable | Owner | Status
Week 1 | Apr 15–18 | Performance | Cap API query limits (tasks, clients, projects) | Dev | ✅ Done
Week 1 | Apr 15–18 | Performance | Fix N+1 DB query in task blocks check | Dev | ✅ Done
Week 1 | Apr 15–18 | Performance | Reduce initial page load from 2000→500 rows | Dev | ✅ Done
Week 1 | Apr 15–18 | Pagination | Add pagination to Clients, Inbox, Recurring views | Dev | ✅ Done
Week 1 | Apr 15–18 | QA | End-to-end smoke test on all major flows | Dev | 🔄 Pending
Week 1 | Apr 19–21 | Infra | Set up Supabase connection pooler (PgBouncer) | DevOps | 🔄 Pending
Week 1 | Apr 19–21 | Infra | Enable Supabase rate limiting / WAF rules | DevOps | 🔄 Pending
Week 1 | Apr 19–21 | Infra | Configure Next.js caching headers for static assets | Dev | 🔄 Pending
Week 2 | Apr 22–25 | Payments | Razorpay — integrate subscription plan checkout | Dev | ⬜ Todo
Week 2 | Apr 22–25 | Payments | Razorpay — webhook handler for plan upgrades | Dev | ⬜ Todo
Week 2 | Apr 22–25 | Payments | Razorpay — billing portal (invoices, cancel) | Dev | ⬜ Todo
Week 2 | Apr 26–28 | WhatsApp | WhatsApp Business API — credentials & sandbox setup | Dev | ⬜ Todo
Week 2 | Apr 26–28 | WhatsApp | Task assignment notifications via WhatsApp | Dev | ⬜ Todo
Week 2 | Apr 26–28 | WhatsApp | Due-date reminders via WhatsApp (daily 9 AM) | Dev | ⬜ Todo
Week 3 | Apr 29–May 1 | Client Portal | Magic link setup flow for new clients | Dev | ⬜ Todo
Week 3 | Apr 29–May 1 | Client Portal | Partner/client view — task visibility + upload only | Dev | ⬜ Todo
Week 3 | Apr 29–May 1 | Client Portal | Client portal: document checklist view | Dev | ⬜ Todo
Week 3 | May 2–4 | UI Polish | Dark mode audit — fix any remaining hardcoded colors | Dev | ⬜ Todo
Week 3 | May 2–4 | UI Polish | Mobile responsive pass on all major pages | Dev | ⬜ Todo
Week 3 | May 2–4 | QA | Load testing (k6 or locust) — simulate 100 concurrent users | QA | ⬜ Todo
Week 4 | May 5–7 | Content | Demo video recording — core task workflow | Marketing | ⬜ Todo
Week 4 | May 5–7 | Content | Demo video recording — CA compliance module | Marketing | ⬜ Todo
Week 4 | May 5–7 | Content | Promotional video — 90-second product overview | Marketing | ⬜ Todo
Week 4 | May 8–9 | Marketing | Landing page update with new screenshots + pricing | Marketing | ⬜ Todo
Week 4 | May 8–9 | Marketing | Email announcement draft (existing users + waitlist) | Marketing | ⬜ Todo
Week 4 | May 10–11 | Marketing | Social media posts — LinkedIn, Twitter, Instagram scheduled | Marketing | ⬜ Todo
Week 5 | May 12–13 | Final QA | Full regression test — all modules | Dev + QA | ⬜ Todo
Week 5 | May 12–13 | Final QA | Performance benchmark — page load < 2s (LCP) | Dev | ⬜ Todo
Week 5 | May 14 | Launch Prep | Backup DB snapshot, deploy to production | DevOps | ⬜ Todo
Week 5 | May 14 | Launch Prep | Warm-up caches, verify Inngest cron jobs running | Dev | ⬜ Todo
Week 5 | May 15 | 🚀 LAUNCH | Send launch announcement emails | Marketing | 🚀 Launch Day
Week 5 | May 15 | 🚀 LAUNCH | Post on all social media channels | Marketing | 🚀 Launch Day
Week 5 | May 15 | 🚀 LAUNCH | Monitor error rates, DB performance, Inngest queue | Dev | 🚀 Launch Day

## ⚡ Performance Fixes
PERFORMANCE AUDIT — Planora
Severity | Area | File / Route | Issue | Fix Applied | Status
HIGH | API — Tasks | app/api/tasks/route.ts | No max limit cap — clients could request 10,000+ rows | Capped at 500 rows; added offset/range pagination | ✅ Fixed
HIGH | API — Projects | app/api/projects/route.ts | No max limit cap on project query | Capped at 500 rows | ✅ Fixed
HIGH | API — Clients | app/api/clients/route.ts | No limit or pagination — full table scan for large orgs | Added limit (500) + offset pagination params | ✅ Fixed
HIGH | DB — N+1 | app/api/tasks/[id]/route.ts | Blocks check fired 1 DB query per blocking task (N+1) | Replaced Promise.all loop with single .in() batch query | ✅ Fixed
HIGH | Page Load | app/(app)/tasks/page.tsx | Initial SSR load was .limit(2000) on 4 parallel queries | Reduced to .limit(500) per query | ✅ Fixed
HIGH | Page Load | app/(app)/inbox/page.tsx | Initial SSR load was .limit(2000) | Reduced to .limit(500) | ✅ Fixed
HIGH | Pagination | ClientsView.tsx | No pagination — all clients rendered in one grid | Added 50-per-page client-side pagination with Prev/Next | ✅ Fixed
HIGH | Pagination | InboxView.tsx | No pagination — all tasks in each section rendered at once | Added 100-per-section show-more button | ✅ Fixed
HIGH | Pagination | RecurringView.tsx | No pagination — all recurring tasks rendered at once | Added show-more (100 at a time) | ✅ Fixed
HIGH | No Rate Limiting | All API routes | Zero rate limiting — any user can spam any endpoint | TODO: Add Upstash Redis rate limiter in middleware | ⬜ Pending
HIGH | No DB Indexes | Supabase schema | Missing indexes on tasks.assignee_id, parent_task_id, org_id+status | TODO: Add via Supabase migration | ⬜ Pending
MEDIUM | N+1 — Clone | app/api/projects/[id]/clone/route.ts | Cloning tasks loops with individual INSERT + SELECT per task | TODO: Batch insert tasks, batch fetch subtasks | ⬜ Pending
MEDIUM | Heavy Join | app/api/tasks/[id]/approve | 4+ serial DB queries per approval decision | TODO: Combine into fewer queries with joins | ⬜ Pending
MEDIUM | JSONB Index | tasks table | JSONB _blocked_by array containment — no GIN index | TODO: CREATE INDEX on custom_fields using GIN | ⬜ Pending
MEDIUM | Auth Overhead | middleware.ts | supabase.auth.getUser() on every request — no caching | TODO: Cache session token validation (short TTL) | ⬜ Pending
MEDIUM | Large Select | app/api/tasks/[id]/route.ts | SELECT * wildcard fetches all JSONB custom_fields unnecessarily | TODO: Enumerate only needed columns | ⬜ Pending
MEDIUM | CA Tasks Load | app/(app)/tasks/page.tsx | caInstances fetched with no limit (could be thousands) | TODO: Add .limit(500) and lazy-load older instances | ⬜ Pending
MEDIUM | No Caching | All pages | No client-side caching — repeated page visits re-fetch all data | TODO: Implement React Query or SWR for data fetching | ⬜ Pending
LOW | Comments | app/api/tasks/[id]/comments | No limit on comments fetch — tasks with 1000s comments slow | TODO: Add .limit(200) and pagination UI | ⬜ Pending
LOW | Email Burst | lib/inngest/functions/ | 100 task assignments fire 100 emails serially | TODO: Batch to digest, rate-limit sends | ⬜ Pending
LOW | No CDN | next.config.ts | Static assets not cached with CDN headers | TODO: Configure cache-control headers + Vercel CDN | ⬜ Pending

## 🚀 Feature Roadmap
FEATURE ROADMAP — Planora Launch
Feature | Description | Effort | Target Week | Dependencies | Status
Razorpay — Checkout | Replace manual billing with Razorpay subscription checkout (plan pages, upgrade flow) | Large | Week 2 | Razorpay account approved | ⬜ Todo
Razorpay — Webhooks | Handle payment.captured, subscription.charged, subscription.cancelled events to update plan in DB | Medium | Week 2 | Razorpay Checkout | ⬜ Todo
Razorpay — Billing Portal | Show invoices, current plan, cancel subscription in /settings/billing | Medium | Week 2 | Razorpay Webhooks | ⬜ Todo
WhatsApp Notifications | Task-assigned and due-date-reminder messages via WhatsApp Business API | Large | Week 2 | WA Business account | ⬜ Todo
WhatsApp Opt-in | User phone number field + opt-in toggle in /settings/notifications | Small | Week 2 | WhatsApp Notifications | ⬜ Todo
Magic Link — Client Setup | Email link for new clients; on click, sets password + lands in client portal | Medium | Week 3 | Client portal exists | ⬜ Todo
Partner / Client View | Read-only task + document upload view for clients (no sidebar, no edit) | Large | Week 3 | Magic Link setup | ⬜ Todo
Client Document Checklist | Clients see required documents and can upload inline in their portal | Medium | Week 3 | Partner View | ⬜ Todo
DB Indexes | Add missing Supabase indexes via migration for scalability | Small | Week 1–2 | Supabase access | ⬜ Todo
Rate Limiting | Per-user, per-IP rate limits via Upstash Redis in Next.js middleware | Medium | Week 1–2 | Upstash Redis account | ⬜ Todo
Load Testing | k6 or Locust test suite — simulate 500 concurrent users, identify bottlenecks | Medium | Week 3 | Staging environment | ⬜ Todo
SEO + OG Tags | Add Open Graph meta + structured data to landing page for product hunt | Small | Week 4 | Landing page copy | ⬜ Todo

## 📣 Marketing Plan
MARKETING PLAN — Planora Launch (May 15, 2026)
Channel | Action | Target Audience | Date | Owner | Status
Demo Video | Record 3–5 min walkthrough of core task + approval workflow | CA firms, SMBs | May 5–7 | Marketing | ⬜ Todo
Demo Video — CA Module | Record 2–3 min CA compliance module deep-dive | CA / Tax firms | May 5–7 | Marketing | ⬜ Todo
Promo Video | 90-second snappy product overview for ads + social | General B2B | May 5–7 | Marketing | ⬜ Todo
Screenshot Pack | 10 polished screenshots for landing page & ads | All segments | May 3–4 | Design | ⬜ Todo
LinkedIn | Post launch announcement + article on "how Planora helps CA firms" | CA professionals | May 15 | Founder | ⬜ Todo
LinkedIn | Share behind-the-scenes build story (product journey) 3 days before launch | Early adopters | May 12 | Founder | ⬜ Todo
Twitter / X | Tweet thread: "We built a task manager for CA firms because..." | Tech + CA community | May 15 | Founder | ⬜ Todo
Instagram Reels | 30-sec demo reel + promo video | Gen-Z professionals | May 15 | Marketing | ⬜ Todo
WhatsApp Broadcast | Message to existing network of CA contacts | CA professionals | May 14 | Founder | ⬜ Todo
Email — Waitlist | Launch announcement to waitlist: features + discount code | Waitlist | May 15 | Marketing | ⬜ Todo
Email — Existing Users | Changelog email to beta users: new features + thank you | Beta users | May 14 | Marketing | ⬜ Todo
Product Hunt | Submit product listing (prepare 2 weeks before) | Tech community | May 15 | Founder | ⬜ Todo
Reddit | Post in r/Accounting, r/smallbusiness: "We built X for CA firms" | CA + SMB | May 15–16 | Founder | ⬜ Todo
CA Community Groups | Share in WhatsApp / Telegram groups of CAs and accountants | CA firms | May 15 | Founder | ⬜ Todo
Google Ads (optional) | Run search ads for "task manager for CA firms" | CA professionals | May 15+ | Marketing | ⬜ Todo
LinkedIn Ads (optional) | Sponsored post targeting finance + accounting professionals | B2B decision makers | May 15+ | Marketing | ⬜ Todo

## 🐛 Issue Reports Guide
WHERE DO USER-REPORTED ISSUES GO?
Button location | Header bar — the "speech bubble with +" icon (MessageSquarePlus)
How to trigger | Click the icon in the top-right header; type message, attach screenshot, submit
API endpoint | POST /api/report-issue
Storage — text | Saved to Supabase table: issue_reports (columns: id, org_id, reporter_id, message, page_url, attachments, status, created_at)
Storage — files | Uploaded to Supabase Storage bucket: attachments, path: issue-reports/{timestamp}-{filename}
Default status | open (you can manually update to resolved / in_progress in Supabase dashboard)
How to view | Go to Supabase → Table Editor → issue_reports. Filter by status=open to see all open reports.
Tip | Add a Supabase Webhook or trigger to email yourself on INSERT to issue_reports for instant alerts
Current limitation | No in-app issue tracking dashboard — plan to build one in post-launch iteration

## ✅ Launch Checklist
LAUNCH CHECKLIST — May 15, 2026
Category | Checklist Item | Done? | Notes
Performance | API query limits capped (500 max) | ☐
Performance | N+1 DB queries fixed in task blocks | ☐
Performance | DB indexes added for org_id, assignee_id, parent_task_id | ☐ | Run Supabase migration
Performance | Rate limiting enabled in middleware | ☐ | Needs Upstash Redis
Performance | Load test passed (100+ concurrent users) | ☐ | Use k6 or locust
Payments | Razorpay integration working (checkout + webhooks) | ☐
Payments | Plan upgrades reflected immediately in UI | ☐
Payments | Failed payment handling tested | ☐
WhatsApp | Task-assigned WA notification sending correctly | ☐
WhatsApp | Due-date reminders at 9 AM IST | ☐
Client Portal | Magic link setup flow tested end-to-end | ☐
Client Portal | Partner view renders correctly (no edit access) | ☐
Email | All Inngest email functions verified (task assigned, approval, reminder) | ☐
Email | FROM email domain verified in Resend | ☐ | Check DNS records
Auth | OAuth (Google) login tested in production | ☐
Auth | Magic link login tested in production | ☐
UI / UX | Dark mode audit complete (no hardcoded hex backgrounds) | ☐
UI / UX | Mobile responsive on all main pages | ☐
SEO | Landing page has correct OG tags and meta description | ☐
Infra | Custom domain configured + SSL active | ☐ | sng-adwisers.com
Infra | Supabase DB backup snapshot taken before launch | ☐
Infra | Inngest cron jobs (7 AM IST) verified in production | ☐
Infra | Error monitoring (Sentry or similar) configured | ☐
Content | Demo video uploaded and linked on landing page | ☐
Content | Promo video ready for social media | ☐
Marketing | Product Hunt listing scheduled for 12:01 AM PST May 15 | ☐
Marketing | Email to waitlist + existing users drafted and scheduled | ☐
Marketing | Social posts pre-scheduled in tool (Buffer/Hootsuite) | ☐
Marketing | WhatsApp broadcast list ready | ☐
Post-Launch | Monitoring dashboard open on launch day | ☐ | Check Supabase metrics
Post-Launch | On-call person assigned for launch day | ☐